## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a user, I want to be able to select a character that matches my personality so that I can feel like I am a part of the game. | 2 | Medium | Incomplete | 2 | NOTE: As a team we decided that weekly meetings followed by weekly sprints were the best course of action that would work well for us
2 | As a user I want to be able to see what all the potential moves are for each round so that I can know where to go without knowing the rules. | 2 | Medium | Incomplete | 1
3 | As a user I want to be able to receive character power ups so that gameplay can vary from match to match. | 5 | Low | Incomplete | 4
4 | As a user I want to be able to see what my previous scores were so that I can be notified when I make a new high score. | 4 | Low | Incomplete | 2
5 | As a user I want to be able to set my font size so that I can see the wordings more clearly if they are too small. | 3 | Low | Incomplete | 1
6 | As a user I want to be able to play the game on my mobile phone so that I can play the game while I am traveling as a passenger to school. | 3 | High | Incomplete | 2
7 | As a user I want to be able to use the device of my preference so that I can play the game no matter where I am. | 3 | High | Incomplete | 2
8 | As a user I want to be able to save a game setting on one device and persist it on all my other devices so that I don't have to set the game setting each time I play from a different device. |  | Low | Incomplete | 1
9 | As a user I want to be able to see whose turn it is to play so that I am aware when I should attempt my turn on the board. | 3 | Medium | Incomplete | 1
10 | As a user I want to be able to see the scores of the other plays in addition to mine so that I can be aware of if I am winning or losing and by how much. | 3 | High | Incomplete | 1
11 | As a user I want to hear a sound so that I will know it is my turn when I am not paying attention. | 4 | Low | Incomplete | 2
12 | As a user I want to be able to select a board theme so that I can change up the look when one gets old. | 5 | Low | Incomplete | 3
13 | As a user I want to be able to time my matches so that I can know how fast I won/lost. | 5 | Low | Incomplete | 1
14 | As a user I want the ability to forfeit so that I can get into another game faster | 5 | Medium | Incomplete | 2
15 | As a user I want the option to play on bigger/smaller boards so that the game can be played with different paces. | 4 | Low | Incomplete | 2
16 | As a user I want the ability to make tournament lobbies so that I can make tournaments for my friends. | 6 | Low | Incomplete | 3
17 | As a user I want an ELO ladder so that I can see how I perform against other players. | 6 | Low | Incomplete | 2
18 | As a user I want a downloadable game log so that I can review it later. | 5 | Low | Incomplete | 3
19 | As a user I want an indicator to highlight each player's most recent move so that I can strategize even if I look away. | 3 | High | Incomplete | 2
20 | As a user I want shareable links so that I can send them to my friends. | 3 | High | Incomplete | 2
21 | As a user I want a chat feature so that I can communicate with the other players. | 3 | High | Incomplete | 4
22 | As a user I want people who take too long to make a move to be skipped so that the game doesn’t stop. | 3 | High | Incomplete | 2
23 | As a user I want unlockable content so that I can feel like there’s a goal. | 5 | Low | Incomplete | 4
24 | As a user I want an interactive tutorial so that I can pick up the game easier. | 5 | Medium | Incomplete | 4
25 | As a player I want to be able to host custom games of Squared with custom rules (i.e., time allotted per turn, size of game board, etc.) so that I can add variety to the game. | 4 | Medium | Incomplete | 3
26 | As a player I want the option to spectate ongoing games of Squared so that I can observe other player’s strategies and enjoy the game even when I’m not playing it. | 5 | Low | Incomplete | 2
27 | As a player I want the ability to customize the layout and positioning of the game board, chat and other features relative to one another so that I can observe the game in a way that is comfortable and convenient for me. | 4 | Low | Incomplete | 2
28 | As an online player I want a rematch button so that I can immediately start another game with the same opponent. | 4 | Medium | Incomplete | 2
29 | As a competitive player I want the ability to record matches so that I can review my gameplay. | 5 | Low | Incomplete | 2
30 | As an online player I want the ability to save chat logs made during gameplay so that I can look over messages sent to me by other players after I’ve finished playing with them. | 3 | Low | Incomplete | 1
31 | As a developer, I want a board my users can interact with | 2 | High | Complete | 3
32 | As a developer, I want a function in the API that can provide randomized dice rolls | 2 | High | Complete | 1
33 | As a developer, I want a function in the API to check if a move is valid | 2 | High | Complete | 2
34 | As a developer, I want the frontend to send the tapped section on the board to the API for processing | 3 | High | Complete | 2
35 | As a developer, I want the frontend to respond to the API and move the player accordingly | 3 | High | Complete | 2
36 | As a developer, I want the user icons to be created and implemented | 2 | High | Complete | 2
37 | As a developer, I want the games to be in a linked list data structure for processing | 3 | High | Complete | 2
38 | As a developer, I'd like a basic API template in place to develop | 2 | High | Complete | 1
39 | As a developer, I'd like a basic ReactJS project structure with the development environment fully implemented | 2 | High | Complete | 2
40 | As a developer, I want the first drafts of the main routes | 2 | High | Complete | 2
41 | As a player, I would like to be able to see my score, so that I will be aware of I am winning the game. | 2 | Medium | Complete | 3
42 | As a user I want a chat feature so that I can communicate with the other players. | 3 | High | Complete | 3
43 | As a user I would like to be able to log into the game from any device so that my game progress can be tracked. | 3 | High | Complete | 3
44 | As a user I would like inappropriate chat messages to be censored | 4 | medium | Complete | 2