## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
36 | As a developer, I want the user icons to be created and implemented | Create icons and implement them into the game itself | 2 | 2 | Developer | 2 | 2 | Keijaoh Campbell: 100%
33 | As a developer, I want a function in the API to check if a move is valid | Add a function to the backend to verify moves | 3 | 3 | Developer | 2 | 2 | Jacob Lorenzo: 50% Tyler Walker: 50%
34 | As a developer, I want the frontend to send the tapped section on the board to the API for processing | Send square information to backend on click | 3 | 3 | Developer | 2 | 2 | Tyler Walker: 100%
35 | As a developer, I want the frontend to respond to the API and move the player accordingly | Update player's position in real-time by querying the server for game status | 3 | 3 | Developer | 2 | 2 | Tyler Walker: 100%
41 | As a player, I would like to be able to see my score, so that I will be aware of I am winning the game. | Create a scoreboard for the game | 3 | 3 | Player | 2 | 3 | Tyler Walker: 50% Keijaoh Campbell: 50%
42 | As a user I want a chat feature so that I can communicate with the other players. | Update the Chat Component to use an array of objects instead of hard coded values. Update the CSS to fix spacing issues. | 3 | 3 | Player | 2 | 2 | Keijaoh Campbell: 100%
43 | As a user I would like to be able to log into the game from any device so that my game progress can be tracked. | Create Login Form and componets. Create resuable Form element handle form changes, submission and validation. | 3 | 3 | User | 2 | 2 | Keijaoh Campbell: 100%
44 | As a user I would like inappropriate chat messages to be censored | Create a method that takes in an object with the message, username, and use id | 4 | 4 | user | 2 | 2 | Shea Keegan 100%
31 | As a developer, I want a board my users can interact with | Create ReactJS, CSS and HTML elements that display a grid-like board onto the SQUARED game interface. Create front-end methods that display characters on the board. Create back-end methods that track player positions and determine whether the spots that players want to go to are valid or not. | 2 | 5 | Developer | 3 | 3 | Tyler Walker: 66% Keijaoh Campbell 33%
32 | As a developer, I want a function in the API that can provide randomized dice rolls | Produce a back-end function that generates a random number between 1 and 6 (representing a dice roll), updates the game object accordingly, and allows the player who rolled that roll to move that number of spaces. | 2 | 5 | Developer | 1 | 1 | Jacob Lorenzo: 100%
37 | As a developer, I want the games to be in a linked list data structure for processing | Create methods that assign specific games to specific IDs internally. Create a linked list that stores all active games within them. | 3 | 5 | Developer | 2 | 2 | Tyler Walker: 50% Keijaoh Campbell: 50%
38 | As a developer, I'd like a basic API template in place to develop | Create ReactJS templates for front-end components that can interact with back-end databases and stored data. | 2 | 5 | Developer | 1 | 1 | Keijaoh Campbell: 100%
39 | As a developer, I'd like a basic ReactJS project structure with the development environment fully implemented | Organize external website assets (such as images and videos), ReactJS scripts, CSS files and subsystems of SQUARED in a manner that is compliant with common ReactJS and web development practices and enables Team Squared to efficiently and easily develop new interfaces for the SQUARED website. | 2 | 5 | Developer | 2 | 2 | Keijaoh Campbell: 100%
40 | As a developer, I want the first drafts of the main routes | Use the @app.route() Flask decorator to specify important routes that will need to be taken by end users frequently during gameplay as a means of updating the SQUARED game and allowing the website to be navigated properly. Implement game-specific routes that update game components, such as /diceroll for letting players roll dice, and /verify for verifying the validity of player moves. | 2 | 5 | Developer | 2 | 2 | Jacob Lorenzo: 50% Tyler Walker: 50%