## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
35 | As a developer, I want the user icons to be created and implemented | Create icons and implement them into the game itself | 2 | 2 | Developer | 2 | 2 | Keijaoh Campbell: 100%
36 | As a developer, I want the games to in a linked list data structure for processing | Create game object | 2 | 2 | Developer | 2 | 2 | Tyler Walker: 100%
31 | As a developer, I want a board my users can interact with |  | 2 | 2 | Developer | 2 | 2 | Jeffrey Fosgate: 100%
32 | As a developer, I want a function in the API that can provide randomized dice rolls |  | 2 | 2 | Developer | 1 | 1 | Jacob Lorenzo: 100%
37 | As a developer, I'd like a basic API template in place to develop | Create the flask app and sample routes | 2 | 2 | Developer | 1 | 1 | Shea Keegan: 100%
38 | As a developer, I'd like a basic ReactJS project structure with the development environment fully implemented | Generate React file structure, set up boilerplate code, get NPM packages setup, implement react views | 2 | 2 | Developer | 2 | 2 | Keijaoh Campbell: 100%
39 | As a developer, I want the first drafts of the main routes | Add routes to landing page, provide visual drafts, implement drafts | 2 | 2 | Developer | 2 | 2 | Jeffrey Fosgate: 50%, Keijaoh Campbell 50%